## Instructions
The Minnesota Pollution Control Agency (MPCA) developed this table to consolidate all timeframes listed in the National Pollutant Discharge Elimination System (NPDES)/Stat Disposal System (SDS) Construction Stormwater (CSW) Permit listed in one place. Local stormwater staff in regulated municipal seperate storm sewer systems (MS4) communities can use this table to know the expectations for municipally owned or operated projects and for construction sites they are inspecting.

## Timelines
Timeframe | 30 days before work starts | 7 days before work starts | Immediate | 24 hours | End of next business day | 72 hours | 7 days | 14 days | Within 30 days of event | 3 years | Other timeframes
Activity | Submit a copy of the stormwater pollution prevention plan (SWPPP) to the MPCA if construction will disturb 50 or more acres and may discharge to a special or impaired water located within a one aerial mile radius | Submit permit application to the MPCA (see 30 days before work starts) | Initiate soil stabilization where construction activity has permanently or temporarily stopped and will not resume for 14 days, or for 7 days if the site discharges to a special or impaired water | Complete stabilization of exposed soil that is within 200 feet (ft) of a Public Waters that has a “work in water restrictions” during specified fish spawning times | Repair or replace nonfunctional best management practices (BMPs) | Be available onsite - staff who are trained in conducting inspections or responsible for the SWPPP | Conduct inspections of the entire site | Complete stabilization of exposed soils after construction has permanently or temporarily stopped in that portion of the site (see 7 days if the site discharges to a special or impaired water within a one mile aerial radius) | Submit a Permit Modification Form if ownership changes | Retain records after the permit is closed | Before land disturbing activities begin: install sediment control practices on downgradient perimeters and upgradient of buffer zones
|  |  | Replace downgradient sediment controls that were adjusted or removed to accommodate short-term activity | Stabilize ditch bottoms within 200 ft of a surface water or property line (see 14 day requirements for remaining portion) | Repair or replace perimeter control devices when they are nonfunctional | Drain and remove sediment from sedimentation basins when sediment reaches 1/2 the storage volume | Amend the SWPPP if inspections identify that changes are needed | Complete stabilization of temporary or permanent ditches or swales after connection to surface water or property edge (see 24 hour requirements for bottom 200 ft) | Submit the Notice of Termination (NOT) form to end permit coverage when the project is finished and final stabilization is complete | Complete refresher training in erosion prevention, sediment control, permanent stormwater management, and/or the Construction Stormwater Permit | For sites that construction activity has ceased and there is permanent cover on all exposed soils: inspect the site during non‐frozen ground conditions at least once a month for 12 months
|  |  |  | Stabilize temporary or permanent ditches or swales that were being used as sediment containment during construction but are no longer used | Repair or replace perimeter control devices when sediment reaches 1/2 the device height | Provide the SWPPP, including all certificates, reports, records, or other information, to federal, state, and local officials, upon request | Remove all deltas and sediment in surface waters and restabilize exposed soil |  |  |  | If sediment is present in the streets: Remove sediment at a frequency sufficient to minimize off‐site impacts
|  |  |  | Install energy dissipation at pipe outlets |  |  | Complete stabilization of soils for projects within one mile aerial radius of a special or impaired water, where work has temporarily or permanently ceased on any portion of the site
Inspect the site if 0.5 inches or more of rain falls within a 24 hour period
Record all inspections and maintenance activities
Inspect site after runoff occurs when construction was suspended due to frozen conditions
Remove tracked sediment from all paved surfaces